## Report
Tasks by Functional Area | Commencement Date | Scheduled Completion Date | Task Duration (weeks) | Weeks elapsed to date | % Time Elapsed since start date | Planned % Completion | Actual % Completion | % Achievement of Target
1) System Analysis | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 5.6% | 5.6% | 100%
2) System Design | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 14.75% | 14.75% | 100%
3) Technical Support | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 7% | 4% | 57.14%
4) Development | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 7% | 7.915% | 113.1%
5) Project Administration | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 7% | 7.2% | 102.9%
6) System Testing | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 7.5% | 7.5% | 100%
7) User Acceptance Testing | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 7.4% | 7.4% | 100%
8) User Training | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 7% | 6.5% | 92.86%
9) User Documentation | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 13.8% | 14% | 101.4%
Project Summary | 1997-03-01 | 1997-12-01 | 39.2857 | 3.5714 | 9.091% | 8.741% | 8.763% | 100.3%
Notes:
1) Status as at: | 1997-03-26

## Overview
| Schedule Information |  |  |  | Budget Info |  | % Completions |  |  |  | % Ahead/behind
Tasks by Area of Responsibility | Commencement Date | Scheduled Completion Date | Total Working Days | Elapsed Working Days | Budgeted Level of Effort | Person days booked to date | % Time Elapsed since start date | % Budget Days used to date | Planned % Completion | Actual % Completion | Time Index | Budget Index | Overall Performance Index
1) Project Leader (Code A) |  |  | 180.0595 | 16.369 | 135 | 4 | 9.091% | 5% | 9.5% | 9.5% | 4.5% | 40% | 22.25%
System Analysis - 10101A | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 20 | 1 | 9.091% | 5% | 7% | 7% | -23% | 40% | 8.5%
System Design - 10102A | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 1 | 9.091% | 20% | 14% | 14% | 54% | -30% | 12%
Project Administration - 10120A | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 105 | 1 | 9.091% | 0.9524% | 2% | 2% | -78% | 110% | 16%
User Acceptance Testing - 10108A | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 1 | 9.091% | 20% | 15% | 15% | 65% | -25% | 20%
2) Customer Care Co-ordinator (Code K) |  |  | 180.0595 | 16.369 | 389 | 94 | 9.091% | 2.857% | 0.087597 | 0.092825 | 2.107% | 110% | 56.05%
System Analysis - 10101K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 35 | 1 | 9.091% | 2.857% | 6% | 6% | -34% | 110% | 38%
System Design - 10102K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 1 | 9.091% | 20% | 15% | 15% | 65% | -25% | 20%
Customer Care Development - Sub Total | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 277 | 88 | 9.091% | 31.77% | 6.318% | 9.977% | 9.75% | -68.59% | -29.42%
Project Administration - 10120K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 13 | 1 | 9.091% | 7.692% | 8% | 8% | -12% | 4% | -4%
System Testing - 10107K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 22 | 1 | 9.091% | 4.545% | 7% | 7% | -23% | 54% | 15.5%
User Acceptance Testing - 10108K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 32 | 1 | 9.091% | 3.125% | 5% | 5% | -45% | 60% | 7.5%
User Documentation - 10109K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 1 | 9.091% | 20% | 14% | 14% | 54% | -30% | 12%
3) Billing Co-ordinator (Code E) |  |  | 180.0595 | 16.369 | 513 | 19 | 9.091% | 2.857% | 0.089341 | 0.089341 | -1.725% | 110% | 54.14%
System Analysis - 10101E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 35 | 1 | 9.091% | 2.857% | 6% | 6% | -34% | 110% | 38%
System Design - 10102E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 1 | 9.091% | 20% | 15% | 15% | 65% | -25% | 20%
Billing Development - Sub Total | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 401 | 13 | 9.091% | 3.242% | 7.538% | 7.538% | -17.08% | 132.5% | 57.73%
Project Administration - 10120E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 13 | 1 | 9.091% | 7.692% | 8% | 8% | -12% | 4% | -4%
System Testing - 10107E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 22 | 1 | 9.091% | 4.545% | 7% | 7% | -23% | 54% | 15.5%
User Acceptance Testing - 10108E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 32 | 1 | 9.091% | 3.125% | 5% | 5% | -45% | 60% | 7.5%
User Documentation - 10109E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 1 | 9.091% | 20% | 14% | 14% | 54% | -30% | 12%
4) Interface Co-ordinator (Code L) |  |  | 180.0595 | 16.369 | 261 | 13 | 9.091% | 2.857% | 0.091633 | 0.091633 | 0.7959% | 75% | 37.9%
System Analysis - 10101L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 35 | 1 | 9.091% | 2.857% | 5% | 5% | -45% | 75% | 15%
System Design - 10102L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 1 | 9.091% | 20% | 15% | 15% | 65% | -25% | 20%
Interfaces Development - Sub Total | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 150 | 7 | 9.091% | 4.667% | 9.143% | 9.143% | 0.5714% | 95.92% | 48.24%
Project Administration - 10120L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 13 | 1 | 9.091% | 7.692% | 9% | 9% | -1% | 17% | 8%
System Testing - 10107L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 21 | 1 | 9.091% | 4.762% | 6% | 6% | -34% | 26% | -4%
User Acceptance Testing - 10108L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 32 | 1 | 9.091% | 3.125% | 6% | 6% | -34% | 92% | 29%
User Documentation - 10109L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 1 | 9.091% | 20% | 14% | 14% | 54% | -30% | 12%
5) Business Analyst - (Code T) |  |  | 180.0595 | 16.369 | 105 | 5 | 9.091% | 2.857% | 0.08 | 0.08 | -12% | 40% | 14%
System Analysis - 10101T | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 35 | 1 | 9.091% | 2.857% | 4% | 4% | -56% | 40% | -8%
Development - 10103T | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 35 | 1 | 9.091% | 2.857% | 5% | 5% | -45% | 75% | 15%
System Testing - 10107T | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 10 | 1 | 9.091% | 10% | 10% | 10% | 10% | 0% | 5%
User Acceptance Testing - 10108T | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 20 | 1 | 9.091% | 5% | 6% | 6% | -34% | 20% | -7%
User Documentation 10109T | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 1 | 9.091% | 20% | 15% | 15% | 65% | -25% | 20%
6) Technical Analysts (Code U) |  |  | 180.0595 | 16.369 | 45 | 2 | 9.091% | 2.857% | 0.085 | 0.07 | -23% | 40% | 8.5%
Technical Support - 10129U | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 35 | 1 | 9.091% | 2.857% | 7% | 4% | -56% | 40% | -8%
User Training - 10125U | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 10 | 1 | 9.091% | 10% | 10% | 10% | 10% | 0% | 5%
7) Client Services Consultants (Code V) |  |  | 180.0595 | 16.369 | 100 | 9 | 9.091% | 2% | 0.08 | 0.08 | -12% | 50% | 19%
User Training - 10125V | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 50 | 1 | 9.091% | 2% | 4% | 3% | -67% | 50% | -8.5%
User Documentation - 10109V | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 50 | 8 | 9.091% | 16% | 12% | 13% | 43% | -18.75% | 12.12%
8) Senior Consultant |  |  | 180.0595 | 16.369 | 90 | 8 | 9.091% | 8.889% | 0.08 | 0.09 | -1% | 1.25% | 0.125%
Project Administration - 10120W | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 90 | 8 | 9.091% | 8.889% | 8% | 9% | -1% | 1.25% | 0.125%
Project Summary | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 3276 | 308 | 9.091% | 9.402% | 8.741% | 8.763% | -3.609% | -6.795% | -5.202%
Notes: | Start | Finish | Total | Past | LOE | T/St | Time | Budg. | Plan | Actual | Time | Budg. | O/all
1) StABCs as at: | 1997-03-26 |  |  |  | Elapsed Time Calculation
2) Working days are based on 7.5 hours per day. |  |  |  |  | Working days per week: | [5 empty] | 5
[5 empty] | Public Holidays per year: | [5 empty] | 11
[5 empty] | Effective Working days per week: | [5 empty] | 4.5833
[5 empty] | Factor: | [5 empty] | 0.65476

## Development
|  | Schedule Information |  |  |  | Budget |  | % Completions |  |  |  | % Ahead/behind
Task # | Development Tasks | Commencement Date | Scheduled Completion Date | Total Working Days | Elapsed Working Days | Budgeted Level of Effort | Person days booked to date | % Time Elapsed since start date | % Budget Days used to date | Planned % Completion | Actual % Completion | Time Index | Budget Index | Overall Performance Index
| 1) Customer Care (Code K) | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 277 | 88 | 9.091% | 31.77% | 6.318% | 9.977% | 9.75% | -68.59% | -29.42%
2 | Data Partitioning Security Stamp - 1020#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 20 | 4 | 9.091% | 20% | 6% | 6.5% | -28.5% | -67.5% | -48%
9 | Credit Information - POSID only - 1090#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 4 | 9.091% | 80% | 15% | 12.5% | 37.5% | -84.38% | -23.44%
10b | Add Yellow Pages Data Screens - 1100#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 4 | 9.091% | 80% | 9% | 12.5% | 37.5% | -84.38% | -23.44%
11b | Quantity Billing - Online Content - 1110#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 3 | 4 | 9.091% | 133.3% | 8% | 14.5% | 59.5% | -89.12% | -14.81%
12 | Calling Card PIN - ABC calc. - 1120#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 2 | 4 | 9.091% | 200% | 7% | 15.5% | 70.5% | -92.25% | -10.88%
16 | Contract Screen Work Around - 1160#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 10 | 4 | 9.091% | 40% | 5% | 9.5% | 4.5% | -76.25% | -35.88%
8 | Address Formatting - 1080#K (also task 17) | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 10 | 4 | 9.091% | 40% | 5% | 9.5% | 4.5% | -76.25% | -35.88%
22b | Work unit entry & presentation on Work Order - 1220#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 50 | 4 | 9.091% | 8% | 5% | 3.3% | -63.7% | -58.75% | -61.22%
24 | Access Service Request from Carrier - work around - 1240#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 10 | 4 | 9.091% | 40% | 5% | 9.5% | 4.5% | -76.25% | -35.88%
29 | CABS Billing Provisioning - 1290#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 4 | 9.091% | 26.67% | 5% | 7.7% | -15.3% | -71.12% | -43.21%
31 | LIDB Electronic Interface - 13F0#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 4 | 9.091% | 26.67% | 5% | 7.7% | -15.3% | -71.12% | -43.21%
31 | E911 Tape Interface - 13G0#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 4 | 9.091% | 26.67% | 5% | 7.7% | -15.3% | -71.12% | -43.21%
31 | LM Berry Yellow Pages Annual Interface - 13Q0#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 4 | 9.091% | 26.67% | 5% | 7.7% | -15.3% | -71.12% | -43.21%
33 | FAA Bill Telemanagement Reports - CC content - 1330#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 4 | 4 | 9.091% | 100% | 5% | 13.5% | 48.5% | -86.5% | -19%
34 | GSA Bill Telemanagement Reports - CC content - 1340#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 4 | 4 | 9.091% | 100% | 5% | 13.5% | 48.5% | -86.5% | -19%
46 | Mass Activate Network guides - 1460#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 10 | 4 | 9.091% | 40% | 5% | 9.5% | 4.5% | -76.25% | -35.88%
57 | Flags to exempt tax fees at ANI level - Online content - 1570#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 20 | 4 | 9.091% | 20% | 5% | 6.5% | -28.5% | -67.5% | -48%
58 | Misc. Customer Care Data Elements - 1580#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 11 | 4 | 9.091% | 36.36% | 5% | 9% | -1% | -75.25% | -38.12%
59 | Credit Card Expiry Report - 1590#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 4 | 9.091% | 80% | 5% | 12.5% | 37.5% | -84.38% | -23.44%
60 | Add Res. Ass.Fnctnlty - Online Content - 1600#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 3 | 4 | 9.091% | 133.3% | 5% | 14.5% | 59.5% | -89.12% | -14.81%
61 | Diff. betwn two types of calling cards - 1610#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 5 | 4 | 9.091% | 80% | 5% | 12.5% | 37.5% | -84.38% | -23.44%
62 | Linked Dependencies - 1620#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 40 | 4 | 9.091% | 10% | 14% | 3.9% | -57.1% | -61% | -59.05%
| 2) Billing (Code E) | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 401 | 13 | 9.091% | 3.242% | 7.538% | 7.538% | -17.08% | 132.5% | 57.73%
11b | Quantity Billing - Online /Billing Content - 1110#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 1 | 9.091% | 6.667% | 6% | 6% | -34% | -10% | -22%
19 | Toll advice forms - 1190#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 20 | 1 | 9.091% | 5% | 9% | 9% | -1% | 80% | 39.5%
31 | Visa Bank Receivable Transfer - 13H0#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 1 | 9.091% | 6.667% | 8% | 8% | -12% | 20% | 4%
31 | FMS Interface - Flat file - 13L0#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 40 | 1 | 9.091% | 2.5% | 7% | 7% | -23% | 180% | 78.5%
31 | FIS Interface - Flat File - 13M0#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 40 | 1 | 9.091% | 2.5% | 7% | 7% | -23% | 180% | 78.5%
31 | Check Writer Interface - Flat File - 13N0#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 50 | 1 | 9.091% | 2% | 7% | 7% | -23% | 250% | 113.5%
34 | GSA Bill Telemanagement Reports - Billing Content - 1340#K | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 36 | 1 | 9.091% | 2.778% | 7% | 7% | -23% | 152% | 64.5%
35 | Bill Format Customization - 1350#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 50 | 1 | 9.091% | 2% | 7% | 7% | -23% | 250% | 113.5%
36 | Post Bill Changes to accomodate Bill Changes - 1360#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 50 | 1 | 9.091% | 2% | 7% | 7% | -23% | 250% | 113.5%
40 | Bill on Diskette - 1400#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 1 | 9.091% | 6.667% | 7% | 7% | -23% | 5% | -9%
56 | On-Line screen listing of entered payments - 1560#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 10 | 1 | 9.091% | 10% | 7% | 7% | -23% | -30% | -26.5%
57 | Flags to exempt tax fees at ANI level - Billing content - 1570#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 30 | 1 | 9.091% | 3.333% | 5% | 5% | -45% | 50% | 2.5%
60 | Add Res. Ass.Fnctnlty - Billing Content - 1600#E | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 30 | 1 | 9.091% | 3.333% | 14% | 14% | 54% | 320% | 187%
| 3) Interfaces (Code L) | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 150 | 7 | 9.091% | 4.667% | 9.143% | 9.143% | 0.5714% | 95.92% | 48.24%
47 | EDR Receipt - EMI - 13C0#L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 1 | 9.091% | 6.667% | 5% | 5% | -45% | -25% | -35%
47 | GCI Extract - EMI - 13D0#L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 1 | 9.091% | 6.667% | 15% | 15% | 65% | 125% | 95%
31 | AT&T Alaskom Extract - 13E0#L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 1 | 9.091% | 6.667% | 9% | 9% | -1% | 35% | 17%
31 | Lock Box feed from Municipality - 13i0#L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 1 | 9.091% | 6.667% | 9% | 9% | -1% | 35% | 17%
31 | Download to ABC Autodialer for collections - 13J0#L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 1 | 9.091% | 6.667% | 6% | 6% | -34% | -10% | -22%
37 | Conversion - 1370#L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 60 | 1 | 9.091% | 1.667% | 6% | 6% | -34% | 260% | 113%
55 | Ability to return calls to Carrier - 1550#L | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 15 | 1 | 9.091% | 6.667% | 14% | 14% | 54% | 110% | 82%
Development Summary |  | 1997-03-01 | 1997-12-01 | 180.0595 | 16.369 | 828 | 108 | 9.091% | 13.04% | 7.167% | 9.083% | -0.08333% | -30.36% | 6.226%
| Notes: | Start | Finish | Total | Past | LOE | T/St | Time | Budg. | Plan | Actual | Time | Budg. | O/all
| 1) StABCs as at: | 1997-03-26 |  |  |  | Elapsed Time Calculation
| 2) Working days are based on 7.5 hours per day. |  |  |  |  | Working days per week: | [5 empty] | 5
[6 empty] | Public Holidays per year: | [5 empty] | 11
[6 empty] | Effective Working days per week: | [5 empty] | 4.5833
[6 empty] | Factor: | [5 empty] | 0.65476

## Data
Code |  |  | Item | Activity | Co-ordinated by: | 1999-09-09 | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Totals
ABC- | 10101 | A | General | System Analysis | Project Leader | 1 | [11 empty] | 1
ABC- | 10101 | E | General | System Analysis | Billing | 1 | [11 empty] | 1
ABC- | 10101 | K | General | System Analysis | Customer Care | 1 | [11 empty] | 1
ABC- | 10101 | L | General | System Analysis | Interfaces | 1 | [11 empty] | 1
ABC- | 10101 | T | General | System Analysis | Business Analyst | 1 | [11 empty] | 1
ABC- | 10102 | A | General | System Design | Project Leader | 1 | [11 empty] | 1
ABC- | 10102 | E | General | System Design | Billing | 1 | [11 empty] | 1
ABC- | 10102 | K | General | System Design | Customer Care | 1 | [11 empty] | 1
ABC- | 10102 | L | General | System Design | Interfaces | 1 | [11 empty] | 1
ABC- | 10103 | T | Development Phase | Business Analysis | Business Analyst | 1 | [11 empty] | 1
ABC- | 10107 | E | General | System Testing | Billing | 1 | [11 empty] | 1
ABC- | 10107 | K | General | System Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 10107 | L | General | System Testing | Interfaces | 1 | [11 empty] | 1
ABC- | 10107 | T | General | System Testing | Business Analyst | 1 | [11 empty] | 1
ABC- | 10108 | A | General | User Acceptance Testing | Project Leader | 1 | [11 empty] | 1
ABC- | 10108 | E | General | User Acceptance Testing | Billing | 1 | [11 empty] | 1
ABC- | 10108 | K | General | User Acceptance Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 10108 | L | General | User Acceptance Testing | Interfaces | 1 | [11 empty] | 1
ABC- | 10108 | T | General | User Acceptance Testing | Business Analyst | 1 | [11 empty] | 1
ABC- | 10109 | E | Billing | User Documentation | Billing | 1 | [11 empty] | 1
ABC- | 10109 | K | Customer Care | User Documentation | Customer Care | 1 | [11 empty] | 1
ABC- | 10109 | L | Interfaces | User Documentation | Interfaces | 1 | [11 empty] | 1
ABC- | 10109 | T | Business Analyst | User Documentation | Business Analyst | 1 | [11 empty] | 1
ABC- | 10109 | V | Client Services Consultants | User Documentation | Project Leader | 1 | [11 empty] | 1
ABC- | 10115 | Z | General | Management Time - Billable | Project Leader | 1 | [11 empty] | 1
ABC- | 10118 | Z | General | Travel - Billable | Project Leader | 1 | [11 empty] | 1
ABC- | 10120 | A | General | Project Administration | Project Leader | 1 | [11 empty] | 1
ABC- | 10120 | E | General | Project Administration | Billing | 1 | [11 empty] | 1
ABC- | 10120 | K | General | Project Administration | Customer Care | 1 | [11 empty] | 1
ABC- | 10120 | L | General | Project Administration | Interfaces | 1 | [11 empty] | 1
ABC- | 10120 | W | General | Project Administration | Senior Consultant | 1 | [11 empty] | 1
ABC- | 10125 | U | Technical Analysts | User Training | Project Leader | 1 | [11 empty] | 1
ABC- | 10125 | V | Client Services Consultants | User Training | Project Leader | 1 | [11 empty] | 1
ABC- | 10129 | U | By Technical Analysts | Technical Support | Project Leader | 1 | [11 empty] | 1
ABC- | 10163 | Z | General | Meetings | Project Leader | 1 | [11 empty] | 1
ABC- | 10165 | Z | General | Management Time - non-Billable | Project Leader | 1 | [11 empty] | 1
ABC- | 10168 | Z | General | Travel - non-Billable | Project Leader | 1 | [11 empty] | 1
ABC- | 10199 | Z | CBP work o/s scope of LOE | CBP Development | Project Leader | 1 | [11 empty] | 1
ABC- | 10203 | K | Data Partitioning | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 10204 | K | Data Partitioning | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 10205 | K | Data Partitioning | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 10206 | K | Data Partitioning | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 10803 | K | Address Formatting | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 10804 | K | Address Formatting | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 10805 | K | Address Formatting | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 10806 | K | Address Formatting | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 10903 | K | Credit Information | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 10904 | K | Credit Information | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 10905 | K | Credit Information | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 10906 | K | Credit Information | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 11003 | K | Add Yellow Page Data Screens | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 11004 | K | Add Yellow Page Data Screens | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 11005 | K | Add Yellow Page Data Screens | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 11006 | K | Add Yellow Page Data Screens | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 11203 | K | Calling Card PIN | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 11204 | K | Calling Card PIN | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 11205 | K | Calling Card PIN | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 11206 | K | Calling Card PIN | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 11603 | K | Contract Screen Work Around | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 11604 | K | Contract Screen Work Around | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 11605 | K | Contract Screen Work Around | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 11606 | K | Contract Screen Work Around | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 11903 | E | Toll Advice Forms | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 11904 | E | Toll Advice Forms | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 11905 | E | Toll Advice Forms | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 11906 | E | Toll Advice Forms | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 12203 | K | Work Unit Entry | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 12204 | K | Work Unit Entry | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 12205 | K | Work Unit Entry | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 12206 | K | Work Unit Entry | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 12403 | K | Access Srvice Rqst frm Carrier | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 12404 | K | Access Srvice Rqst frm Carrier | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 12405 | K | Access Srvice Rqst frm Carrier | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 12406 | K | Access Srvice Rqst frm Carrier | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 12903 | K | CABS Billing | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 12904 | K | CABS Billing | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 12905 | K | CABS Billing | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 12906 | K | CABS Billing | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 13303 | K | FAA Bill T/mgmt Reports | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 13304 | K | FAA Bill T/mgmt Reports | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 13305 | K | FAA Bill T/mgmt Reports | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 13306 | K | FAA Bill T/mgmt Reports | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 13403 | E | GSA Bill T/mgmt Reports | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 13403 | K | GSA Bill T/mgmt Reports | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 13404 | E | GSA Bill T/mgmt Reports | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 13404 | K | GSA Bill T/mgmt Reports | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 13405 | E | GSA Bill T/mgmt Reports | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 13405 | K | GSA Bill T/mgmt Reports | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 13406 | E | GSA Bill T/mgmt Reports | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 13406 | K | GSA Bill T/mgmt Reports | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 13503 | E | Bill Format Customization | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 13504 | E | Bill Format Customization | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 13505 | E | Bill Format Customization | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 13506 | E | Bill Format Customization | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 13603 | E | P/Bil Chngs to acc. Bill Changes | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 13604 | E | P/Bil Chngs to acc. Bill Changes | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 13605 | E | P/Bil Chngs to acc. Bill Changes | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 13606 | E | P/Bil Chngs to acc. Bill Changes | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 13703 | L | Conversion | Program Requirements | Interfaces | 1 | [11 empty] | 1
ABC- | 13704 | L | Conversion | Program Analysis & Design | Interfaces | 1 | [11 empty] | 1
ABC- | 13705 | L | Conversion | Coding/Programming | Interfaces | 1 | [11 empty] | 1
ABC- | 13706 | L | Conversion | Unit Testing | Interfaces | 1 | [11 empty] | 1
ABC- | 13C03 | L | Interfaces-EDR Receipt | Program Requirements | Interfaces | 1 | [11 empty] | 1
ABC- | 13C04 | L | Interfaces-EDR Receipt | Program Analysis & Design | Interfaces | 1 | [11 empty] | 1
ABC- | 13C05 | L | Interfaces-EDR Receipt | Coding/Programming | Interfaces | 1 | [11 empty] | 1
ABC- | 13C06 | L | Interfaces-EDR Receipt | Unit Testing | Interfaces | 1 | [11 empty] | 1
ABC- | 13D03 | L | Interfaces - GCI Extract | Program Requirements | Interfaces | 1 | [11 empty] | 1
ABC- | 13D04 | L | Interfaces - GCI Extract | Program Analysis & Design | Interfaces | 1 | [11 empty] | 1
ABC- | 13D05 | L | Interfaces - GCI Extract | Coding/Programming | Interfaces | 1 | [11 empty] | 1
ABC- | 13D06 | L | Interfaces - GCI Extract | Unit Testing | Interfaces | 1 | [11 empty] | 1
ABC- | 13E03 | L | Interfaces - AT&T Alaskom Ext. | Program Requirements | Interfaces | 1 | [11 empty] | 1
ABC- | 13E04 | L | Interfaces - AT&T Alaskom Ext. | Program Analysis & Design | Interfaces | 1 | [11 empty] | 1
ABC- | 13E05 | L | Interfaces - AT&T Alaskom Ext. | Coding/Programming | Interfaces | 1 | [11 empty] | 1
ABC- | 13E06 | L | Interfaces - AT&T Alaskom Ext. | Unit Testing | Interfaces | 1 | [11 empty] | 1
ABC- | 13F03 | K | Interfaces - LIDB | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 13F04 | K | Interfaces - LIDB | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 13F05 | K | Interfaces - LIDB | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 13F06 | K | Interfaces - LIDB | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 13G03 | K | Interfaces - E911 | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 13G04 | K | Interfaces - E911 | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 13G05 | K | Interfaces - E911 | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 13G06 | K | Interfaces - E911 | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 13H03 | E | Interfaces - Visa Bank rec. t/f | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 13H04 | E | Interfaces - Visa Bank rec. t/f | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 13H05 | E | Interfaces - Visa Bank rec. t/f | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 13H06 | E | Interfaces - Visa Bank rec. t/f | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 13i03 | L | Interfaces - L/box fd frm Muni. | Program Requirements | Interfaces | 1 | [11 empty] | 1
ABC- | 13i04 | L | Interfaces - L/box fd frm Muni. | Program Analysis & Design | Interfaces | 1 | [11 empty] | 1
ABC- | 13i05 | L | Interfaces - L/box fd frm Muni. | Coding/Programming | Interfaces | 1 | [11 empty] | 1
ABC- | 13i06 | L | Interfaces - L/box fd frm Muni. | Unit Testing | Interfaces | 1 | [11 empty] | 1
ABC- | 13J03 | L | Interfaces - D/load to ABC a/dial | Program Requirements | Interfaces | 1 | [11 empty] | 1
ABC- | 13J04 | L | Interfaces - D/load to ABC a/dial | Program Analysis & Design | Interfaces | 1 | [11 empty] | 1
ABC- | 13J05 | L | Interfaces - D/load to ABC a/dial | Coding/Programming | Interfaces | 1 | [11 empty] | 1
ABC- | 13J06 | L | Interfaces - D/load to ABC a/dial | Unit Testing | Interfaces | 1 | [11 empty] | 1
ABC- | 13L03 | E | Interfaces - FMS | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 13L04 | E | Interfaces - FMS | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 13L05 | E | Interfaces - FMS | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 13L06 | E | Interfaces - FMS | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 13M03 | E | Interfaces - FIS | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 13M04 | E | Interfaces - FIS | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 13M05 | E | Interfaces - FIS | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 13M06 | E | Interfaces - FIS | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 13N03 | E | Interfaces - Check Writer | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 13N04 | E | Interfaces - Check Writer | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 13N05 | E | Interfaces - Check Writer | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 13N06 | E | Interfaces - Check Writer | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 13Q03 | K | Interfaces - Annual LMB Batch | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 13Q04 | K | Interfaces - Annual LMB Batch | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 13Q05 | K | Interfaces - Annual LMB Batch | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 13Q06 | K | Interfaces - Annual LMB Batch | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 13X03 | A | Interfaces - General | Program Requirements | Project Leader | 1 | [11 empty] | 1
ABC- | 13X03 | K | Interfaces - General | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 13X03 | E | Interfaces - General | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 13X03 | L | Interfaces - General | Program Requirements | Interfaces | 1 | [11 empty] | 1
ABC- | 13X04 | A | Interfaces - General | Program Analysis & Design | Project Leader | 1 | [11 empty] | 1
ABC- | 13X04 | K | Interfaces - General | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 13X04 | E | Interfaces - General | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 13X04 | L | Interfaces - General | Program Analysis & Design | Interfaces | 1 | [11 empty] | 1
ABC- | 14003 | E | Bill on Diskette | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 14004 | E | Bill on Diskette | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 14005 | E | Bill on Diskette | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 14006 | E | Bill on Diskette | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 14603 | K | Mass Activate Network Guides | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 14604 | K | Mass Activate Network Guides | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 14605 | K | Mass Activate Network Guides | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 14606 | K | Mass Activate Network Guides | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 15403 | K | Special Billing No. Processing | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 15404 | K | Special Billing No. Processing | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 15405 | K | Special Billing No. Processing | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 15406 | K | Special Billing No. Processing | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 15503 | L | Ability to return calls to carrier | Program Requirements | Interfaces | 1 | [11 empty] | 1
ABC- | 15504 | L | Ability to return calls to carrier | Program Analysis & Design | Interfaces | 1 | [11 empty] | 1
ABC- | 15505 | L | Ability to return calls to carrier | Coding/Programming | Interfaces | 1 | [11 empty] | 1
ABC- | 15506 | L | Ability to return calls to carrier | Unit Testing | Interfaces | 1 | [11 empty] | 1
ABC- | 15603 | E | Onln scrn lstg of entered pymts | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 15604 | E | Onln scrn lstg of entered pymts | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 15605 | E | Onln scrn lstg of entered pymts | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 15606 | E | Onln scrn lstg of entered pymts | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 15703 | E | Flgs to exmpt tax fees at ANI lvl | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 15703 | K | Flgs to exmpt tax fees at ANI lvl | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 15704 | E | Flgs to exmpt tax fees at ANI lvl | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 15704 | K | Flgs to exmpt tax fees at ANI lvl | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 15705 | E | Flgs to exmpt tax fees at ANI lvl | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 15705 | K | Flgs to exmpt tax fees at ANI lvl | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 15706 | E | Flgs to exmpt tax fees at ANI lvl | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 15706 | K | Flgs to exmpt tax fees at ANI lvl | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 15803 | K | Misc. Cust. Care Data Elements | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 15804 | K | Misc. Cust. Care Data Elements | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 15805 | K | Misc. Cust. Care Data Elements | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 15806 | K | Misc. Cust. Care Data Elements | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 15903 | K | Credit Card Expiry Report | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 15904 | K | Credit Card Expiry Report | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 15905 | K | Credit Card Expiry Report | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 15906 | K | Credit Card Expiry Report | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 16003 | E | Add Res. Addrs Functionality | Program Requirements | Billing | 1 | [11 empty] | 1
ABC- | 16003 | K | Add Res. Addrs Functionality | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 16004 | E | Add Res. Addrs Functionality | Program Analysis & Design | Billing | 1 | [11 empty] | 1
ABC- | 16004 | K | Add Res. Addrs Functionality | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 16005 | E | Add Res. Addrs Functionality | Coding/Programming | Billing | 1 | [11 empty] | 1
ABC- | 16005 | K | Add Res. Addrs Functionality | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 16006 | E | Add Res. Addrs Functionality | Unit Testing | Billing | 1 | [11 empty] | 1
ABC- | 16006 | K | Add Res. Addrs Functionality | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 16103 | K | Diff. btwn 2 types of c/cards | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 16104 | K | Diff. btwn 2 types of c/cards | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 16105 | K | Diff. btwn 2 types of c/cards | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 16106 | K | Diff. btwn 2 types of c/cards | Unit Testing | Customer Care | 1 | [11 empty] | 1
ABC- | 16203 | K | Linked Dependencies | Program Requirements | Customer Care | 1 | [11 empty] | 1
ABC- | 16204 | K | Linked Dependencies | Program Analysis & Design | Customer Care | 1 | [11 empty] | 1
ABC- | 16205 | K | Linked Dependencies | Coding/Programming | Customer Care | 1 | [11 empty] | 1
ABC- | 16206 | K | Linked Dependencies | Unit Testing | Customer Care | 1 | [11 empty] | 1

## Chart Data
Internal Analysis Chart
Responsibility | Linear | Financial | Overall
Project Leader | 4.5% | 40% | 22.25%
Customer Care | 2.107% | 110% | 56.05%
Billing | -1.725% | 110% | 54.14%
Interfaces | 0.7959% | 75% | 37.9%
Business Analyst | -12% | 40% | 14%
Technical Analysts | -23% | 40% | 8.5%
Client Services | -12% | 50% | 19%
Senior Consultant | -1% | 1.25% | 0.125%
WHOLE PROJECT | -3.609% | -6.795% | -5.202%
Customer Report Chart
Function | % Variance
System Analysis | 100%
System Design | 100%
Technical Support | 57.14%
Development | 113.1%
Project Administration | 102.9%
System Testing | 100%
User Acceptance Testing | 100%
User Training | 92.86%
User Documentation | 101.4%
WHOLE PROJECT | 100.3%